## BUD 2017
2. 2017 Budget per activity
Activity number | Activities | Cost | Cost | écart | %ge
|  | (in Euros) | (in Euros)
Composante 1
1. | IT/RARS Expert | 21000 | 21000 | 0 | 100%
2. | RARS Expert (Technical Assistance) | 54000 | 0 | 54000 | 0%
3. | Consultation for RARS Design study | 0 | 0 | 0 | 0%
4. | Preparation of the RARS hosting site infrastructure and establishing MoU with hosting sites | 40000 | 0 | 40000 | 0%
5. | On-site inspection and coordination meeting with RARS hosting sites (Estabishment of RARS network) | 19000 | 0 | 19000 | 0%
| Sub Total Composante 1 | 134000 | 21000 | 113000 | 15.67%
Composante 2
6 | NWP FORECASTER | 21000 | 8750 | 12250 | 41.67%
7 | NWP FORECASTER ASSISTANT | 15000 | 5500 | 9500 | 36.67%
8 | NWP modeller | 23400 | 0 | 23400 | 0%
9 | NWP System Engineer/IT specialist | 21000 | 8750 | 12250 | 41.67%
10 | NWP Expert (Technical Assistant) | 54000 | 0 | 54000 | 0%
11 | Procurement and installation of NWP hardware and software infrastructure (HPC system and customized software) | 0 | 0 | 0 | 0%
12 | NWP Capabilities at ACMAD(Travels & DSA) | 19000 | 0 | 19000 | 0%
| Sub Total Composante 2 | 153400 | 23000 | 130400 | 14.99%
Composante 3
13 | NWP Communities (Travel& DSA) | 19000 | 0 | 19000 | 0%
| Sub Total Composante 3 | 19000 |  | 19000 | 0% | 134000 | 27.41%
| Composante 4 |  |  | 0 |  | 153400 | 31.38%
14 | Project Manager | 24600 | 24600 | 0 | 100% | 19000 | 3.887%
15 | project Assistant | 13200 | 13200 | 0 | 100% | 182400 | 37.32%
16 | Monitoring & évaluation Officer | 16200 | 6030 | 10170 | 37.22% | 488800 | 100%
17 | Finance & Administration Officer | 16200 | 16200 | 0 | 100%
18 | Procurement Spécialist | 16200 | 7290 | 8910 | 45%
19 | Communication Officer | 15000 | 6750 | 8250 | 45%
20 | Communication & WEB site service | 10000 | 0 | 10000 | 0%
21 | Travels & DSA | 14000 | 0 | 14000 | 0%
22 | Consommable | 12000 | 4455.48 | 7544.52 | 37.13%
| Sub Total Composante 4 | 137400 | 78525.48 | 58874.52 | 57.15%
| CONTINGENCY |  |  | 0 |  |  | 488800
23 | LANCEMENT DU PROJET | 15000 | 0 | 15000 | 0%
24 | STEERING COMITE MEETING | 30000 | 26867.18 | 3132.82 | 89.56%
| Sub Total CONTINGENCY | 45000 | 26867.18 | 18132.82 | 59.7%
| TOTAL BUDGET PROJET SAWIDRA 2017 | 488800 | 149392.66 | 339407.34 | 30.56%
24 | Contribution ACMAD EN Nature | 17728 | 45817 | -28089 | 258.4%
|  |  |  | 0 | 0% | -28089
| TOTAL BUDGET PROJET SAWIDRA 2017 | 506528 | 195209.66 | 311318.34 | 38.54%

## BUDGET 2018
2. 2018 Budget per activity/Composante
Activity number | Activities | Cost | Exécution | Ecart
|  | (in Euros) | (in Euros) | (in Euros)
Composante 1
1. | IT/RARS Expert | 42000 | 24500 | 17500 | 58.33%
2 | Procurement and instalation of antenna | 1600000 | 0 | 1600000 | 0%
3 | RARS Expert (Technical Assistance) | 108000 | 0 | 108000 | 0%
4 | RARS Design study | 120000 | 72124 | 47876 | 60.1%
5 | Preparation of the RARS hosting site | 40000 | 0 | 40000 | 0%
6 | Travel (flight & DSA) | 19000 | 12234 | 6766 | 64.39%
| Sub Total Composante 1 | 1929000 | 108858 | 1820142 | 5.643%
| Composante 2 |  |  | 0
7 | NWP FORECASTER | 42000 | 24500 | 17500 | 58.33% | 1929000 | 50.21% | 52.03%
8 | NWP FORECASTER ASSISTANT | 30000 | 17500 | 12500 | 58.33% | 1017800 | 26.49% | 27.45%
9 | NWP modeller | 46800 | 18980 | 27820 | 40.56% | 299700 | 7.801% | 8.084%
10 | System Engineer/IT specialist | 42000 | 24500 | 17500 | 58.33% | 460800 | 11.99% | 12.43%
11 | Recruitment of International NWP Expert (Technical Assistant) | 108000 | 0 | 108000 | 0% | 3707300 | 96.5%
12 | Procurement and installation of NWP hardware and software infrastructure | 600000 | 0 | 600000 | 0% | 134431 | 3.499% | 1
13 | customised software | 20000 | 0 | 20000 | 0% | 3841731 | 100%
14 | HPC maintenance | 20000 | 0 | 20000 | 0%
15 | NWP related Telecommunication | 30000 | 3078 | 26922 | 10.26%
2160 | Training for trainers | 12000 | 0 | 12000 | 0%
17 | NWP Capabilities at ACMAD(Travels & DSA) | 19000 |  | 19000 | 0%
18 | HPC operation | 48000 | 0 | 48000 | 0%
| Sub Total Composante 2 | 1017800 | 88558 | 929242 | 8.701%
0
| Composante 3 |  |  | 0
24 | NWP forum | 173500 | 32757 | 140743 | 18.88%
25 | DRR Specialist outlook forum | 17100 | 17100 | 0 | 100%
26 | Product Harmonisation meeting | 17100 | 0 | 17100 | 0%
27 | Data Assimilationand NWP Training | 54000 | 25688 | 28312 | 47.57%
28 | Value Added Training for DRR specialist | 19000 | 0 | 19000 | 0%
29 | NWP Communities (Travel& DSA) | 19000 |  | 19000 | 0%
| Sub Total Composante 3 | 299700 | 75545 | 224155 | 25.21%
Composante 4
30 | Project Manager | 49200 | 28700 | 20500 | 58.33%
31 | project Assistant | 26400 | 15400 | 11000 | 58.33%
32 | Monitoring & évaluation Officer | 32400 | 18900 | 13500 | 58.33%
33 | Finance & Administration Officer | 32400 | 18900 | 13500 | 58.33%
34 | Procurement Spécialist | 32400 | 18900 | 13500 | 58.33%
35 | Communication Officer | 30000 | 17500 | 12500 | 58.33%
36 | Communication & WEB site service | 10000 | 6327 | 3673 | 63.27%
37 | Financial &Accounting Software (Multi-Project (10), Multi-Site (5)) | 25000 | 0 | 25000 | 0%
38 | M&E Software (Multi-Project, Multi-Site) | 20000 | 0 | 20000 | 0%
39 | Financial audit 2017-2018 | 30000 | 0 | 30000 | 0%
| Procedure Manual | 25000 | 0 | 25000 | 0%
| Development of M&E Plan | 7000 | 0 | 7000 | 0%
40 | Travels & DSA | 14000 | 0 | 14000 | 0%
41 | Consommable | 72000 | 16503 | 55497 | 22.92%
| Sub Total Composante 4 | 405800 | 141130 | 264670 | 34.78%
CONTINGENCY
42 | Revue a mi-parcours | 15000 |  | 0 | 0%
43 | STEERING COMITE MEETING | 40000 |  | 0 | 0%
| Sub Total CONTINGENCY | 55000 |  | 0 | 0%
| TOTAL BUDGET PROJET SAWIDRA 2018 | 3707300 | 414091 | 3293209 | 11.17%
2 | Contribution ACMAD EN Nature | 134431 | 52110 |  | 38.76%
| TOTAL BUDGET PROJET SAWIDRA 2018 | 3841731 | 466201 | 3375530 | 12.14%

## Bud projet 1
2. PROJET SAWIDRA Budget per activity/Composante
Activity number | Activities | Cost | Exécution globale | Reliquat budgétaire | Nouveau budget |  |  |  | 2018 | 2019 | 2020
|  | (in Euros) |  |  | Quantité | Unit | Total | Ecart
Composante 1
| IT/RARS Expert | 126000 | 45500 | 80500 | 29 | 3500 | 101500 | 21000
| Procurement and instalation of antenna | 1600000 | 0 | 1600000 | 4 | 400000 | 1600000 | 0
| PDAP design consolidation |  |  |  | 4 | 60000 | 240000 | 240000
| Preparation of the RARS hosting site | 40000 | 0 | 40000 | 4 | 30000 | 120000 | 80000
| RARS Expert (Technical Assistance) | 324000 | 0 | 324000 |  |  | 0 | -324000
| Firme RARS |  |  |  | 1 | 200000 | 200000 | 200000
| RARS Design study (RFS & Telecom) | 120000 | 72124 | 47876 | 2 | 15000 | 30000 | -17876
| RARS Station operation | 30000 |  | 30000 | 4 | 5000 | 20000 | -10000
| RARS Station maintenance for Two years after installation | 120000 |  | 120000 | 8 | 15000 | 120000 | 0
| Telecommunication (2 years10 keuros par station and per year | 80000 |  | 80000 | 2 | 40000 | 80000 | 0
| Training on RARS related SW and operation (e.g. NWP SAF) | 47000 |  | 47000 | 1 | 47000 | 47000 | 0
| ACMAD RARS station operation | 10000 |  | 10000 | 2 | 5000 | 10000 | 0
| Reunions RARS | 0 |  |  | 1 | 20000 | 20000 | 20000
| Travel (flight ticket) | 30000 | 5511 | 24489 | 5 | 1000 | 5000 | -19489
| Travel (DSA) | 27000 | 9483 | 17517 | 25 | 180 | 4500 | -13017
| Sub Total Composante 1 | 2554000 | 132618 | 2421382 |  |  | 2598000 | 176618
Composante 2
| NWP FORECASTER | 84000 | 33250 | 50750 | 29 | 3500 | 101500 | 50750
| NWP FORECASTER ASSISTANT | 60000 | 23000 | 37000 | 29 | 2500 | 72500 | 35500
| NWP modeller | 117000 | 18980 | 98020 | 29 | 3900 | 113100 | 15080
| NWP System Engineer/IT specialist | 126000 | 33250 | 92750 | 29 | 3500 | 101500 | 8750
| Procurement and installation of NWP hardware and software infrastructure | 600000 |  | 600000 | 1 | 600000 | 600000 | 0
| customised software | 20000 |  | 20000 | 0 | 10000 | 0 | -20000
| Recruitment of International NWP Expert (Technical Assistant) | 324000 |  | 324000 |  |  | 0 | -324000
| Firme NWP |  |  |  | 1 | 160000 | 160000 | 160000
| HPC maintenance | 60000 |  | 60000 | 2 | 10000 | 20000 | -40000
| NWP related Telecommunication | 60000 | 3078 | 56922 | 24 | 2000 | 48000 | -8922
| Training for trainers | 12000 |  | 12000 | 1 | 12000 | 12000 | 0
| Travel (flight ticket) | 30000 |  | 30000 | 5 | 1000 | 5000 | -25000
| Travel (DSA) | 27000 |  | 27000 | 25 | 180 | 4500 | -22500
| Electricity | 90000 |  | 90000 | 24 | 3000 | 72000 | -18000
| Achat et entretien de la Climatisation | 30000 |  | 30000 | 24 | 650 | 15600 | -14400
| Groupe Electrogène et amenagement de la salle |  |  |  | 1 | 40000 | 40000 | 40000
| Sub Total Composante 2 | 1640000 | 111558 | 1528442 |  |  | 1365700 | -162742
0
| Composante 3 |  |  | 0
| NWP forum | 347000 | 32757 | 314243 | 2 | 35000 | 70000 | -244243
| DRR Specialist outlook forum | 34200 | 17100 | 17100 | 10 | 20000 | 200000 | 182900
| Product Harmonisation meeting | 34200 | 0 | 34200 | 1 | 24000 | 24000 | -10200
| Data Assimilation and NWP Training | 108000 | 25688 | 82312 | 20 | 2200 | 44000 | -38312
| Value Added Training for DRR specialist | 38000 | 0 | 38000 | 1 | 25000 | 25000 | -13000
| Service climatique aux DRR | 0 | 0 | 0 | 1 | 50000 | 50000 | 50000
| Travel (flight ticket) | 18000 | 0 | 18000 | 5 | 1000 | 5000 | -13000
| Travel (DSA) | 16200 | 0 | 16200 | 25 | 180 | 4500 | -11700
| Sub Total Composante 3 | 595600 | 75545 | 520055 |  |  | 422500 | -97555
Composante 4
| Project Manager | 147600 | 53300 | 94300 | 29 | 4100 | 118900 | 24600
| project Assistant | 79200 | 28600 | 50600 | 29 | 2200 | 63800 | 13200
| Monitoring & évaluation Officer | 97200 | 24930 | 72270 | 29 | 2700 | 78300 | 6030
| Finance & Administration Officer | 97200 | 35100 | 62100 | 29 | 2700 | 78300 | 16200
| Procurement Spécialist | 97200 | 26190 | 71010 | 29 | 2700 | 78300 | 7290
| Communication Officer | 75000 | 24250 | 50750 | 29 | 2500 | 72500 | 21750
| Matériel informatique |  |  | 0 | 1 | 12000 | 12000 | 12000
| Matériel bureautique (photocopieur, imprimante, splits,,,, |  |  | 0 | 0 | 13500 | 0 | 0
| Achat matériel de communication |  |  | 0 | 0 | 14000 | 0 | 0
| Mobilier de bureau |  |  | 0 | 0 | 10000 | 0 | 0
| Financial &Accounting Software +M&E (Multi-Project (10), Multi-Site (5)) | 0 | 0 | 0 | 1 | 25000 | 25000 | 25000
| MS project |  |  | 0 | 1 | 11000 | 11000 | 11000
| Communication & WEB site service | 30000 | 6327 | 23673 | 3 | 12000 | 36000 | 12327
| STEERING COMITE MEETING | 0 | 26867 | -26867 | 2 | 30000 | 60000 | 86867
| reunions COP |  |  | 0 | 2 | 15000 | 30000 | 30000
| Renforcement des capacités du personnel |  |  | 0 | 1 | 0 | 0 | 0
| Financial audit 2017-2018 | 45000 | 0 | 45000 | 4 | 15000 | 60000 | 15000
| Procedure Manual | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Consommable (frais de fonctionnement divers | 0 | 20958 | -20958 | 29 | 3000 | 87000 | 107958
| Development of M&E Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Travel (flight ticket) | 24000 | 0 | 24000 | 5 | 1000 | 5000 | -19000
| Travel (DSA) | 18000 | 0 | 18000 | 25 | 180 | 4500 | -13500
0
| Sub Total Composante 4 | 710400 | 246522 | 463878 |  |  | 820600 | 356722
| CONTINGENCY | 290000 | 0 | 290000 |  |  | 0
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0
| TOTAL BUDGET PROJET SAWIDRA 2018 | 5790000 | 566243 | 5223757 |  |  | 5206800 | 273043
5223757
Note on E10: user: Converti en firme
Note on E18: user: nouvelle lige inserée
Note on E29: user: poste à convertir en firme
Note on H27: user: montant à confirmé avec Abbey et Ali

## BUD MOD
2. PROJET SAWIDRA Budget per activity/Composante
Activity number | Activities | Cost | Exécution globale | Ecart |  | Nouveau budget |  |  |  | 2018 | 2019 | 2020
|  | (in Euros) |  |  |  | Quantité | Unit | Total
Composante 1
1. | IT/RARS Expert | 126000 | 45500 | 80500 | per month | 29 | 3500 | 101500 | 21000
2 | Procurement and instalation of antenna | 1600000 | 0 | 1600000 | per antenna | 4 | 400000 | 1600000 | 0
| PDAP design consolidation |  |  |  | per site | 4 | 60000 | 240000 | 240000
| Preparation of the RARS hosting site | 40000 | 0 | 40000 | per year &station | 4 | 30000 | 120000 | 80000
3 | RARS Expert (Technical Assistance) | 324000 | 0 | 324000 |  |  |  | 0 | -324000
| Firme RARS |  |  |  |  | 1 | 200000 | 200000 | 200000
4 | RARS Design study (RFS & Telecom) | 120000 | 72124 | 47876 | per month | 2 | 15000 | 30000 | -17876
5 | RARS Station operation | 30000 |  | 30000 |  | 4 | 5000 | 20000 | -10000
| RARS Station maintenance for Two years after installation | 120000 |  | 120000 |  | 8 | 15000 | 120000 | 0
| Telecommunication (2 years10 keuros par station and per year | 80000 |  | 80000 |  | 2 | 40000 | 80000 | 0
| Training on RARS related SW and operation (e.g. NWP SAF) | 47000 |  | 47000 |  | 1 | 47000 | 47000 | 0
| ACMAD RARS station operation | 10000 |  | 10000 |  | 2 | 5000 | 10000 | 0
| Reunions RARS | 0 |  |  |  | 1 | 20000 | 20000 | 20000
| Travel (flight ticket) | 30000 | 5511 | 24489 |  | 5 | 1000 | 5000 | -19489
6 | Travel (DSA) | 27000 | 9483 | 17517 |  | 25 | 180 | 4500 | -13017
| Sub Total Composante 1 | 2554000 | 132618 | 2421382 |  |  |  | 2598000 | 176618 | 5.193%
| Composante 2 | [6 empty] | 0
7 | NWP FORECASTER | 84000 | 33250 | 50750 |  | 29 | 3500 | 101500 | 50750
8 | NWP FORECASTER ASSISTANT | 60000 | 23000 | 37000 |  | 29 | 2500 | 72500 | 35500
9 | NWP modeller | 117000 | 18980 | 98020 |  | 29 | 3900 | 113100 | 15080
10 | NWP System Engineer/IT specialist | 126000 | 33250 | 92750 |  | 29 | 3500 | 101500 | 8750
12 | Procurement and installation of NWP hardware and software infrastructure | 600000 |  | 600000 |  | 1 | 600000 | 600000 | 0
13 | customised software | 20000 |  | 20000 |  | 0 | 10000 | 0 | -20000
| Recruitment of International NWP Expert (Technical Assistant) | 324000 |  | 324000 |  | 1 |  | 0 | -324000
| Firme NWP |  |  |  |  | 1 | 160000 | 160000 | 160000
14 | HPC maintenance | 60000 |  | 60000 |  | 2 | 10000 | 20000 | -40000
15 | NWP related Telecommunication | 60000 | 3078 | 56922 |  | 24 | 2000 | 48000 | -8922
2160 | Training for trainers | 12000 |  | 12000 |  | 1 | 12000 | 12000 | 0
| Travel (flight ticket) | 30000 |  | 30000 |  | 5 | 1000 | 5000 | -25000
| Travel (DSA) | 27000 |  | 27000 |  | 25 | 180 | 4500 | -22500
17 | Electricity | 90000 |  | 90000 |  | 24 | 3000 | 72000 | -18000
18 | Achat et entretien de la Climatisation | 30000 |  | 30000 |  | 24 | 650 | 15600 | -14400
| Groupe Electrogène et amenagement de la salle |  |  |  |  | 1 | 40000 | 40000 | 40000
| Sub Total Composante 2 | 1640000 | 111558 | 1528442 |  |  |  | 1365700 | -162742 | 6.802%
|  |  |  | 0 |  |  |  | 0
| Composante 3 |  |  | 0 |  |  |  | 0
24 | NWP forum | 347000 | 32757 | 314243 |  | 2 | 35000 | 70000 | -244243
25 | DRR Specialist outlook forum | 34200 | 17100 | 17100 |  | 10 | 20000 | 200000 | 182900
26 | Product Harmonisation meeting | 34200 | 0 | 34200 |  | 1 | 24000 | 24000 | -10200
27 | Data Assimilation and NWP Training | 108000 | 25688 | 82312 |  | 20 | 2200 | 44000 | -38312
28 | Value Added Training for DRR specialist | 38000 | 0 | 38000 |  | 1 | 25000 | 25000 | -13000
| Service climatique aux DRR | 0 | 0 | 0 |  | 1 | 50000 | 50000 | 50000
| Travel (flight ticket) | 18000 | 0 | 18000 |  | 5 | 1000 | 5000 | -13000
29 | Travel (DSA) | 16200 | 0 | 16200 |  | 25 | 180 | 4500 | -11700
| Sub Total Composante 3 | 595600 | 75545 | 520055 |  |  |  | 422500 | -97555 | 12.68%
Composante 4
30 | Project Manager | 147600 | 53300 | 94300 | per month | 29 | 4100 | 118900 | 24600
31 | project Assistant | 79200 | 28600 | 50600 | per month | 29 | 2200 | 63800 | 13200
32 | Monitoring & évaluation Officer | 97200 | 24930 | 72270 | per month | 29 | 2700 | 78300 | 6030
33 | Finance & Administration Officer | 97200 | 35100 | 62100 | per month | 29 | 2700 | 78300 | 16200
34 | Procurement Spécialist | 97200 | 26190 | 71010 | per month | 29 | 2700 | 78300 | 7290
35 | Communication Officer | 75000 | 24250 | 50750 | per month | 29 | 2500 | 72500 | 21750 | 8907000%
| Matériel informatique |  |  | 0 |  | 1 | 12000 | 12000 | 12000
| Matériel bureautique (photocopieur, imprimante, splits,,,, |  |  | 0 |  | 0 | 13500 | 0 | 0
| Achat matériel de communication |  |  | 0 |  | 0 | 14000 | 0 | 0
| Mobilier de bureau |  |  | 0 |  | 0 | 10000 | 0 | 0
| Financial &Accounting Software +M&E (Multi-Project (10), Multi-Site (5)) | 0 | 0 | 0 |  | 1 | 25000 | 25000 | 25000
| MS project |  |  | 0 |  | 1 | 11000 | 11000 | 11000
36 | Communication & WEB site service | 30000 | 6327 | 23673 |  | 3 | 12000 | 36000 | 12327
| STEERING COMITE MEETING | 0 | 26867 | -26867 |  | 2 | 30000 | 60000 | 86867
| reunions COP |  |  | 0 |  | 2 | 15000 | 30000 | 30000
| Renforcement des capacités du personnel |  |  | 0 |  | 1 | 0 | 0 | 0
39 | Financial audit 2017-2018 | 45000 | 0 | 45000 |  | 4 | 15000 | 60000 | 15000
| Procedure Manual | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Consommable (frais de fonctionnement divers | 0 | 20958 | -20958 |  | 29 | 3000 | 87000 | 107958
| Development of M&E Plan | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
40 | Travel (flight ticket) | 24000 | 0 | 24000 |  | 5 | 1000 | 5000 | -19000
| Travel (DSA) | 18000 | 0 | 18000 |  | 25 | 180 | 4500 | -13500
41 | [7 empty] | 0
| Sub Total Composante 4 | 710400 | 246522 | 463878 |  |  |  | 820600 | 356722 | 34.7%
| CONTINGENCY | 290000 | 0 | 290000 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
| TOTAL BUDGET PROJET SAWIDRA 2018 | 5790000 | 566243 | 5223757 |  |  |  | 5206800 | 273043 | 9.78%
2 | Contribution ACMAD EN Nature | 210000 | [5 empty] | 0 | 16957
| TOTAL BUDGET PROJET SAWIDRA 2018 | 6000000 | [5 empty] | 0
5223757
Note on E10: user: Converti en firme
Note on E18: user: nouvelle lige inserée
Note on E29: user: poste à convertir en firme
Note on I27: user: montant à confirmé avec Abbey et Ali

## Budget proj 2
2. 2018 Budget per activity/Composante
Activity number | Activities | Cost | Exécution globale | Ecart | Nouveau budget |  |  |  | 2018 | 2019 | 2020
|  | (in Euros) |  |  | Quantité | Unit | Total
Composante 1
1. | IT/RARS Expert | 126000 | 45500 | 80500 | 29 | 4740 | 137460
2 | Procurement and instalation of antenna | 1600000 |  | 1600000 | 4 | 500000 | 2000000
| Preparation of the RARS hosting site | 40000 |  | 40000 | 4 | 30000 | 120000
3 | RARS Expert (Technical Assistance) | 324000 |  | 324000 |  |  | 0
| Firme RARS |  |  |  | 1 | 120000 | 120000
4 | RARS Design study | 120000 | 72124 | 47876 | 2 | 15000 | 30000
5 | RARS Station operation | 30000 |  | 30000 | 6 | 5000 | 30000
| RARS Station maintenance for Two years after installation | 120000 |  | 120000 | 8 | 15000 | 120000
| Telecommunication (2 years10 keuros par station and per year | 80000 |  | 80000 | 2 | 40000 | 80000
| Training on RARS related SW and operation (e.g. NWP SAF) | 47000 |  | 47000 | 1 | 47000 | 47000
| ACMAD RARS station operation | 10000 |  | 10000 | 2 | 5000 | 10000
| Reunions RARS | 0 |  |  | 2 | 20000 | 40000
| Travel (flight ticket) | 30000 | 5511 | 24489 | 20 | 1000 | 20000
6 | Travel (DSA) | 27000 | 9483 | 17517 | 100 | 180 | 18000
| Sub Total Composante 1 | 2554000 | 132618 | 2421382 |  |  | 2772460
| Composante 2 |  |  | 0 |  |  | 0
7 | NWP FORECASTER | 84000 | 33250 | 50750 | 29 | 4740 | 137460
8 | NWP FORECASTER ASSISTANT | 60000 | 23000 | 37000 | 29 | 4388 | 127252
9 | NWP modeller | 117000 | 18980 | 98020 | 29 | 4740 | 137460
10 | NWP System Engineer/IT specialist | 126000 | 33250 | 92750 | 29 | 4740 | 137460
| DRM specialist | 0 | 0 | 0 | 24 | 4740 | 113760
12 | Procurement and installation of NWP hardware and software infrastructure | 600000 |  | 600000 | 1 | 700000 | 700000
13 | customised software | 20000 |  | 20000 | 2 | 10000 | 20000
| Recruitment of International NWP Expert (Technical Assistant) | 324000 |  | 324000 |  |  | 0
14 | HPC maintenance | 60000 |  | 60000 | 3 | 20000 | 60000
15 | NWP related Telecommunication | 60000 | 3078 | 56922 | 29 | 2500 | 72500
2160 | Training for trainers | 12000 |  | 12000 | 1 | 12000 | 12000
| Travel (flight ticket) | 30000 |  | 30000 | 30 | 1000 | 30000
| Travel (DSA) | 27000 |  | 27000 | 150 | 180 | 27000
17 | Electricity | 90000 |  | 90000 | 30 | 3000 | 90000
18 | Climatisation | 30000 |  | 30000 | 30 | 1000 | 30000
| inserer d'autres acvités en cas de besoin |  |  |  | 1 | 50000 | 50000
| Sub Total Composante 2 | 1640000 | 111558 | 1528442 |  |  | 1744892
|  |  |  | 0 |  |  | 0
| Composante 3 |  |  | 0 |  |  | 0
24 | NWP forum | 347000 | 32757 | 314243 | 4 | 25000 | 100000 | c
25 | DRR Specialist outlook forum | 34200 | 17100 | 17100 | 16 | 20000 | 320000
26 | Product Harmonisation meeting | 34200 | 0 | 34200 | 4 | 20000 | 80000
27 | Data Assimilationand NWP Training | 108000 | 25688 | 82312 | 28 | 2200 | 61600
28 | Value Added Training for DRR specialist | 38000 | 0 | 38000 | 4 | 10000 | 40000
| Travel (flight ticket) | 18000 | 0 | 18000 | 18 | 1000 | 18000
29 | Travel (DSA) | 16200 | 0 | 16200 | 90 | 180 | 16200
| Sub Total Composante 3 | 595600 | 75545 | 520055 |  |  | 635800
| Composante 4 |  |  | 0 |  |  | 0
30 | Project Manager | 147600 | 53300 | 94300 | 29 | 5269 | 152801
31 | project Assistant | 79200 | 28600 | 50600 | 29 | 4345 | 126005
32 | Monitoring & évaluation Officer | 97200 | 24930 | 72270 | 29 | 4388 | 127252
33 | Finance & Administration Officer | 97200 | 35100 | 62100 | 29 | 4565 | 132385
34 | Procurement Spécialist | 97200 | 26190 | 71010 | 29 | 4388 | 127252
35 | Communication Officer | 75000 | 24250 | 50750 | 29 | 4388 | 127252
| Comptable | [5 empty] | 0
| Matériel informatique |  |  |  | 1 | 18500 | 18500
| Matériel bureautique (photocopieur, imprimante, splits,,,, |  |  |  | 1 | 13500 | 13500
| Achat matériel de communication |  |  |  | 1 | 14000 | 14000
| Mobilier de bureau |  |  |  | 1 | 10000 | 10000
| Financial &Accounting Software +M&E (Multi-Project (10), Multi-Site (5)) | 0 | 0 | 0 | 1 | 52000 | 52000
| MS project |  |  |  | 1 | 11000 | 11000
36 | Communication & WEB site service | 30000 | 6327 | 23673 | 3 | 17000 | 51000
| STEERING COMITE MEETING | 0 | 26867 | -26867 | 3 | 40000 | 120000
| reunions COP |  |  |  | 3 | 20000 | 60000
| Renforcement des capacités du personnel |  |  |  | 1 | 33000 | 33000
39 | Financial audit 2017-2018 | 45000 | 0 | 45000 | 4 | 15000 | 60000
| Procedure Manual | 0 | 0 | 0 | 0 | 0 | 0
| Consommable (frais de fonctionnement divers | 0 | 20958 | -20958 | 30 | 6000 | 180000
| Development of M&E Plan | 0 | 0 | 0 | 0 | 0 | 0
40 | Travel (flight ticket) | 24000 | 0 | 24000 | 30 | 1000 | 30000
| Travel (DSA) | 18000 | 0 | 18000 | 150 | 180 | 27000
41 | [6 empty] | 0
| Sub Total Composante 4 | 710400 | 246522 | 463878 |  |  | 2744547
| CONTINGENCY | 290000 | 0 | 290000 |  |  | 0
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  | 2673942
| TOTAL BUDGET PROJET SAWIDRA 2018 | 5790000 | 566243 | 5223757 |  |  | 7897699
2 | Contribution ACMAD EN Nature | [5 empty] | 0
| TOTAL BUDGET PROJET SAWIDRA 2018 | 5790000 |  |  |  |  | 0
|  |  |  | 5223757 |  |  | 2690899
Note on E9: user: Converti en firme
Note on E17: user: nouvelle lige inserée
Note on E29: user: poste à convertir en firme
Note on H26: user: nouveau recrutement poste non budgétisé au départ
Note on H27: user: montant à confirmé avec Abbey et Ali

## suivi glob
2. 2018 Budget per activity/Composante
Activity number | Activities | Cost | Exécution 2018 | Exécution 2017 | Exécution globale
|  | (in Euros) | (in Euros)
Composante 1
1. | IT/RARS Expert | 42000 | 24500 | 21000 | 45500
2 | Procurement and instalation of antenna | 1600000 | 0 | 0 | 0
3 | RARS Expert (Technical Assistance) | 108000 | 0 | 0 | 0
4 | RARS Design study | 120000 | 72124 | 0 | 72124
5 | Preparation of the RARS hosting site | 40000 | 5511 | 0 | 5511
6 | Travel (flight & DSA) | 19000 | 9483 | 0 | 9483
| Sub Total Composante 1 | 1929000 | 111618 | 21000 | 132618
| Composante 2 |  |  |  | 0
7 | NWP FORECASTER | 42000 | 24500 | 8750 | 33250
8 | NWP FORECASTER ASSISTANT | 30000 | 17500 | 5500 | 23000
9 | NWP modeller | 46800 | 18980 | 0 | 18980
10 | NWP System Engineer/IT specialist | 42000 | 24500 | 8750 | 33250
11 | Recruitment of International NWP Expert (Technical Assistant) | 108000 | 0 | 0 | 0
12 | Procurement and installation of NWP hardware and software infrastructure | 600000 | 0 | 0 | 0
13 | customised software | 20000 | 0 | 0 | 0
14 | HPC maintenance | 20000 | 0 | 0 | 0
15 | NWP related Telecommunication | 30000 | 3078 | 0 | 3078
2160 | Training for trainers | 12000 | 0 | 0 | 0
17 | NWP Capabilities at ACMAD(Travels & DSA) | 19000 |  | 0 | 0
18 | HPC operation | 48000 | 0 | 0 | 0
| Sub Total Composante 2 | 1017800 | 88558 | 23000 | 111558
0
| Composante 3 |  |  |  | 0
24 | NWP forum | 173500 | 32757 | 0 | 32757
25 | DRR Specialist outlook forum | 17100 | 17100 | 0 | 17100
26 | Product Harmonisation meeting | 17100 | 0 | 0 | 0
27 | Data Assimilationand NWP Training | 54000 | 25688 | 0 | 25688
28 | Value Added Training for DRR specialist | 19000 | 0 | 0 | 0
29 | NWP Communities (Travel& DSA) | 19000 |  | 0 | 0
| Sub Total Composante 3 | 299700 | 75545 | 0 | 75545
Composante 4
30 | Project Manager | 49200 | 28700 | 24600 | 53300
31 | project Assistant | 26400 | 15400 | 13200 | 28600
32 | Monitoring & évaluation Officer | 32400 | 18900 | 6030 | 24930
33 | Finance & Administration Officer | 32400 | 18900 | 16200 | 35100
34 | Procurement Spécialist | 32400 | 18900 | 7290 | 26190
35 | Communication Officer | 30000 | 17500 | 6750 | 24250
36 | Communication & WEB site service | 10000 | 6327 | 0 | 6327
37 | Financial &Accounting Software (Multi-Project (10), Multi-Site (5)) | 25000 | 0 | 0 | 0
38 | M&E Software (Multi-Project, Multi-Site) | 20000 | 0 | 0 | 0
39 | Financial audit 2017-2018 | 30000 | 0 | 0 | 0
| Procedure Manual | 25000 | 0 | 0 | 0
| Development of M&E Plan | 7000 | 0 | 0 | 0
40 | Travels & DSA | 14000 | 0 | 0 | 0
41 | Consommable | 72000 | 16503 | 4455.48 | 20958.48
| Sub Total Composante 4 | 405800 | 141130 | 78525.48 | 219655.48
| CONTINGENCY |  |  |  | 0
42 | Revue a mi-parcours | 15000 |  |  | 0
43 | STEERING COMITE MEETING | 40000 |  | 26867.18 | 26867.18
| Sub Total CONTINGENCY | 55000 |  |  | 0
| TOTAL BUDGET PROJET SAWIDRA 2018 | 3707300 | 416851 | 149392.66 | 566243.66
2 | Contribution ACMAD EN Nature |  |  |  | 0
| TOTAL BUDGET PROJET SAWIDRA 2018 | 3707300 | 416851 | 149392.66 | 566243.66

## 2017
2- 2017 Budget par categories
Costs | Unit | # of units | Unit rate | Total Cost | Percent of the total budget | Exécution 2017 | Engagement | total
|  |  | (in EUR) | (in EUR)3
1.PERSONNEL
1.1 Salaries | Per month | 66 | 3072.7273 | 202800 | 40.04% | 118070 | 58.2199
1.1.1 Technical | Per month | 30 | 3380 | 101400 | 20.02% | 44000 | 43.3925
IT/RARS Expert | Per month | 6 | 3500 | 21000 |  | 21000 | 100
NWP Forecaster | Per month | 6 | 3500 | 21000 |  | 8750 | 41.6667
NWP Forecaster Assistant | Per month | 6 | 2500 | 15000 |  | 5500 | 36.6667
NWP modeller | Per month | 6 | 3900 | 23400 |  | 0 | 0 |  | 23000
NWP System Engineer/IT specialist | Per month | 6 | 3500 | 21000 |  | 8750 | 41.6667
1.1.2 Administrative/ support staff | Per month | 36 | 2816.6667 | 101400 | 20.02% | 74070 | 73.0473
Project Manager | Per month | 6 | 4100 | 24600 |  | 24600 | 100
project Assistant | Per month | 6 | 2200 | 13200 |  | 13200 | 100 |  | 74070
Monitoring & évaluation Officer | Per month | 6 | 2700 | 16200 |  | 6030 | 37.2222
Finance & Administration Officer | Per month | 6 | 2700 | 16200 |  | 16200 | 100 |  | 74070 | 0
Procurement Spécialist | Per month | 6 | 2700 | 16200 |  | 7290 | 45
Communication Officer |  | 6 | 2500 | 15000 |  | 6750 | 45
2. GOODS |  | 4 | 10000 | 40000 | 7.897% | 0 | 0
Preparation of the RARS hosting site infrastructure and establishing MoU with hosting sites | per Site | 4 | 10000 | 40000 |  | 0 | 0
Procurement and installation of NWP hardware and software infrastructure (HPC system and customized software) | Full system | 1 | 0 | 0 |  | 0
3. SERVICES |  | 13 | 9076.9231 | 118000 | 23.3% | 0 | 0
RARS Expert (Technical Assistance) | per Month | 6 | 9000 | 54000 |  | 0 | 0
NWP Expert (Technical Assistant) | per Month | 6 | 9000 | 54000 |  | 0 | 0
Communication & WEB site service | Per year | 1 | 10000 | 10000 |  | 0 | 0
4. Operation costs |  | 227.333 | 563.0504 | 127999.94 | 25.27% | 31322.66 | 24.4708
Travel (flight ticket) | Travel | 38 | 1000 | 38000 |  |  | 0
Travel (DSA) | DSA | 183.333 | 180 | 32999.94 |  |  | 0
Consummable | (fuel, vehicle repairs, etc) | 6 | 2000 | 12000 |  | 4455.48 | 37.129
kick off meeting | per meeting | 1 | 15000 | 15000 |  |  | 0
first Steering committee meeting | per meeting | 1 | 30000 | 30000 |  | 26867.18 | 89.5573
|  |  |  | 17728 | 3.5% |  | 0
ACMAD contribt in nature | room,pers, maeriel | 1 | 17728 | 17728 |  | 45817 | 258.4443
Total 2017 budget |  |  |  | 506527.94 | 100% | 195209.66 | 38.5388
Efdb contribution |  |  | 96.5% | 488800
ACMAD contribution in kind |  |  | 3.5% | 17728
Total 2017 Budget |  |  | 100% | 506528
664171.08

## 2018
2- Exécution du Budget2018 par categories
Categories | Unit | # of units | Unit rate | Total Cost | Percent of the total | Exécution 2018 1 | Exécution 2018 2 | Exécution 2018 sub total | Engagements | Exécution 2018 globale | taux de réalisation
|  |  | (in EUR) | (in EUR)3
1.PERSONNEL
1.1 Salaries | Per month | 132 | 3072.7273 | 405600 | 10.56% | 93080 | 115970 | 209050 | 19230 | 228280 | 56.28%
1.1.1 Technical | Per month | 60 | 3380 | 202800 | 5.279% | 42380 | 58870 | 101250 | 8730 | 109980 | 54.23%
IT/RARS Expert | Per month | 12 | 3500 | 42000 |  | 10500 | 12189 | 22689 | 1811 | 24500 | 58.33%
NWP FORECASTER | Per month | 12 | 3500 | 42000 |  | 10500 | 12177 | 22677 | 1823 | 24500 | 58.33%
NWP FORECASTER ASSISTANT | Per month | 12 | 2500 | 30000 |  | 7500 | 8821 | 16321 | 1179 | 17500 | 58.33%
NWP modeller | Per month | 12 | 3900 | 46800 |  | 3380 | 13506 | 16886 | 2094 | 18980 | 40.56%
NWP System Engineer/IT specialist | Per month | 12 | 3500 | 42000 |  | 10500 | 12177 | 22677 | 1823 | 24500 | 58.33%
1.1.2 Administrative/ support staff | Per month | 72 | 2816.6667 | 202800 | 5.279% | 50700 | 57100 | 107800 | 10500 | 118300 | 58.33%
Project Manager | Per month | 12 | 4100 | 49200 |  | 12300 | 12300 | 24600 | 4100 | 28700 | 58.33% | 10.56% | 405600
project Assistant | Per month | 12 | 2200 | 26400 |  | 6600 | 7700 | 14300 | 1100 | 15400 | 58.33% | 58.83% | 2260000
Monitoring & évaluation Officer | Per month | 12 | 2700 | 32400 |  | 8100 | 9450 | 17550 | 1350 | 18900 | 58.33% | 20.71% | 795700
Finance & Administration Officer | Per month | 12 | 2700 | 32400 |  | 8100 | 9450 | 17550 | 1350 | 18900 | 58.33% | 6.403% | 245999.94
Procurement Spécialist | Per month | 12 | 2700 | 32400 |  | 8100 | 9450 | 17550 | 1350 | 18900 | 58.33% | 3.5%
Communication Officer | Per month | 12 | 2500 | 30000 |  | 7500 | 8750 | 16250 | 1250 | 17500 | 58.33% | 100% | 3707299.94
2. GOODS |  | 11 | 205454.5455 | 2260000 | 58.83% | 0 | 0 | 0 | 0 | 0 | 0%
Preparation of the RARS hosting site infrastructure and establishing MoU with hosting sites | per Site | 4 | 10000 | 40000 |  | 0 | 0 | 0 |  | 0 | 0%
Procurement and instalation of antenna | per antenna | 4 | 400000 | 1600000 |  | 0 | 0 | 0 |  | 0 | 0%
Procurement and installation of NWP hardware and software infrastructure (HPC system and customized software) | Full system | 1 | 600000 | 600000 |  | 0 | 0 | 0 |  | 0 | 0%
Customised SW | per SW | 2 | 10000 | 20000 |  | 0 | 0 | 0 |  | 0 | 0%
3. SERVICES |  | 51 | 15601.9608 | 795700 | 20.71% | 26471 | 65149 | 91620 | 65454 | 157074 | 19.74%
RARS Expert (Technical Assistance) | per Month | 12 | 9000 | 108000 |  | 0 | 0 | 0 |  | 0 | 0%
NWP Expert (Technical Assistant) | per Month | 12 | 9000 | 108000 |  | 0 | 0 | 0 |  | 0 | 0%
RARS Design study | per study | 1 | 120000 | 120000 |  | 0 | 6670 | 6670 | 65454 | 72124 | 60.1%
HPC maintenance | Per year | 1 | 20000 | 20000 |  |  |  | 0 |  | 0 | 0%
NWP related Telecommunication | per Month | 12 | 2500 | 30000 |  |  | 3078 | 3078 |  | 3078 | 10.26%
Training for trainers | Training package | 1 | 12000 | 12000 |  |  |  | 0 |  | 0 | 0%
NWP forum | per forum | 1 | 173500 | 173500 |  | 2618 | 30139 | 32757 |  | 32757 | 18.88%
DRR Specialist outlook forum | per forum | 1 | 17100 | 17100 |  | 17100 |  | 17100 |  | 17100 | 100%
Product Harmonisation meeting | per meeting | 1 | 17100 | 17100 |  |  |  | 0 |  | 0 | 0%
Data Assimilationand NWP Training | per training | 1 | 54000 | 54000 |  | 6753 | 18935 | 25688 |  | 25688 | 47.57%
Value Added Training for DRR specialist | per training | 1 | 19000 | 19000 |  |  |  | 0 |  | 0 | 0%
Communication & WEB site service | Per year | 1 | 10000 | 10000 |  | 0 | 6327 | 6327 |  | 6327 | 63.27%
Financial audit 2017-2018 | per audit | 2 | 15000 | 30000 |  |  | 0 | 0 |  | 0 | 0%
Financial &Accounting Software | per SW | 1 | 25000 | 25000 |  |  | 0 | 0 |  | 0 | 0%
M&E Software | per SW | 1 | 20000 | 20000 |  |  | 0 | 0 |  | 0 | 0% |  | 405600 | 10.94%
Development of M&E Plan | per Plan | 1 | 7000 | 7000 |  |  | 0 | 0 |  | 0 | 0% |  | 2260000 | 60.96%
Procedure Manual | Per manuel | 1 | 25000 | 25000 |  |  | 0 | 0 |  | 0 | 0% |  | 795700 | 21.46%
4. Operation costs |  | 248.333 | 990.6051 | 245999.94 | 6.403% | 4601 | 24136.42 | 28737.42 | 2760 | 31497.42 | 12.8% |  | 246000 | 6.636%
Travel (flight ticket) | Travel | 38 | 1000 | 38000 |  | 336 | 5175.19 | 5511.19 |  | 5511.19 | 14.5% |  | 3707300 | 1
Travel (DSA) | DSA | 183.333 | 180 | 32999.94 |  |  | 6723.23 | 6723.23 | 2760 | 9483.23 | 28.74%
HPC operation | per Month | 12 | 4000 | 48000 |  |  |  | 0 |  | 0 | 0%
Consummable (elect,fuel, internet | per Month | 12 | 6000 | 72000 |  | 4265 | 12238 | 16503 |  | 16503 | 22.92%
2nd Steering committee meeting | per stereering | 1 | 40000 | 40000 |  |  |  | 0 |  | 0 | 0%
Mid term meeting |  | 1 | 15000 | 15000 |  |  |  | 0 |  | 0 | 0%
ACMAD contribt |  |  |  | 134461 | 3.5% | 124152 | 205255.42 | 329407.42 | 87444 | 416851.42 | 310%
ACMAD contribt in Kind | room,pers, maeriel | 1 | 1 | 134461 |  | 22333 | 29777 | 52110 |  | 52110 | 38.75%
Total budget |  |  |  | 3841760.94 | 100% | 124152 | 205255.42 | 381517.42 | 87444 | 468961.42 | 12.21%

## cat 2017-2017
2- 2018: xécution budgétaire2017-2018 Budget par categories
Categories | Unit | # of units | Unit rate | Total Cost | Percent of the total | Exécution 2017 | Exécution 2018 1 | Exécution 2018 2 | Exécution 2018 globale | Exécution 2017-2018 globale | Engagements
|  |  | (in EUR) | (in EUR)3
1.PERSONNEL
1.1 Salaries | Per month | 132 | 3072.7273 | 405600 | 10.56% | 118070 | 93080 | 115970 | 209050 | 327120 | 19230 | 346350
1.1.1 Technical | Per month | 60 | 3380 | 202800 | 5.279% | 44000 | 42380 | 58870 | 101250 | 145250 | 8730 | 153980
IT/RARS Expert | Per month | 12 | 3500 | 42000 |  | 21000 | 10500 | 12189 | 22689 | 43689 | 1811 | 45500 | 19230
NWP FORECASTER | Per month | 12 | 3500 | 42000 |  | 8750 | 10500 | 12177 | 22677 | 31427 | 1823 | 33250
NWP FORECASTER ASSISTANT | Per month | 12 | 2500 | 30000 |  | 5500 | 7500 | 8821 | 16321 | 21821 | 1179 | 23000
NWP modeller | Per month | 12 | 3900 | 46800 |  | 0 | 3380 | 13506 | 16886 | 16886 | 2094 | 18980
NWP System Engineer/IT specialist | Per month | 12 | 3500 | 42000 |  | 8750 | 10500 | 12177 | 22677 | 31427 | 1823 | 33250
1.1.2 Administrative/ support staff | Per month | 72 | 2816.6667 | 202800 | 5.279% | 74070 | 50700 | 57100 | 107800 | 181870 | 10500 | 192370
Project Manager | Per month | 12 | 4100 | 49200 |  | 24600 | 12300 | 12300 | 24600 | 49200 | 4100 | 53300 |  | 10.56% | 405600
project Assistant | Per month | 12 | 2200 | 26400 |  | 13200 | 6600 | 7700 | 14300 | 27500 | 1100 | 28600 |  | 58.83% | 2260000
Monitoring & évaluation Officer | Per month | 12 | 2700 | 32400 |  | 6030 | 8100 | 9450 | 17550 | 23580 | 1350 | 24930 |  | 20.71% | 795700
Finance & Administration Officer | Per month | 12 | 2700 | 32400 |  | 16200 | 8100 | 9450 | 17550 | 33750 | 1350 | 35100 |  | 6.403% | 245999.94
Procurement Spécialist | Per month | 12 | 2700 | 32400 |  | 7290 | 8100 | 9450 | 17550 | 24840 | 1350 | 26190 |  | 3.5% | 134461
Communication Officer | Per month | 12 | 2500 | 30000 |  | 6750 | 7500 | 8750 | 16250 | 23000 | 1250 | 24250 |  | 100% | 3841760.94
2. GOODS |  | 11 | 205454.5455 | 2260000 | 58.83% |  | 0 | 0 | 0 | 0 | 0 | 0
Preparation of the RARS hosting site infrastructure and establishing MoU with hosting sites | per Site | 4 | 10000 | 40000 |  | 0 | 0 | 0 | 0 | 0 |  | 0
Procurement and instalation of antenna | per antenna | 4 | 400000 | 1600000 |  | 0 | 0 | 0 | 0 | 0 |  | 0
Procurement and installation of NWP hardware and software infrastructure (HPC system and customized software) | Full system | 1 | 600000 | 600000 |  | 0 | 0 | 0 | 0 | 0 |  | 0
Customised SW | per SW | 2 | 10000 | 20000 |  | 0 | 0 | 0 | 0 | 0 |  | 0
3. SERVICES |  | 51 | 15601.9608 | 795700 | 20.71% |  | 26471 | 65149 | 91620 | 91620 | 65454 | 157074
RARS Expert (Technical Assistance) | per Month | 12 | 9000 | 108000 |  | 0 | 0 | 0 | 0 | 0 |  | 0
NWP Expert (Technical Assistant) | per Month | 12 | 9000 | 108000 |  | 0 | 0 | 0 | 0 | 0 |  | 0
RARS Design study | per study | 1 | 120000 | 120000 |  | 0 | 0 | 6670 | 6670 | 6670 | 65454 | 72124
HPC maintenance | Per year | 1 | 20000 | 20000 |  | 0 |  |  | 0 | 0 |  | 0
NWP related Telecommunication | per Month | 12 | 2500 | 30000 |  | 0 |  | 3078 | 3078 | 3078 |  | 3078
Training for trainers | Training package | 1 | 12000 | 12000 |  | 0 |  |  | 0 | 0 |  | 0
NWP forum | per forum | 1 | 173500 | 173500 |  | 0 | 2618 | 30139 | 32757 | 32757 |  | 32757
DRR Specialist outlook forum | per forum | 1 | 17100 | 17100 |  | 0 | 17100 |  | 17100 | 17100 |  | 17100
Product Harmonisation meeting | per meeting | 1 | 17100 | 17100 |  | 0 |  |  | 0 | 0 |  | 0
Data Assimilationand NWP Training | per training | 1 | 54000 | 54000 |  | 0 | 6753 | 18935 | 25688 | 25688 |  | 25688
Value Added Training for DRR specialist | per training | 1 | 19000 | 19000 |  | 0 |  |  | 0 | 0 |  | 0
Communication & WEB site service | Per year | 1 | 10000 | 10000 |  | 0 | 0 | 6327 | 6327 | 6327 |  | 6327
Financial audit 2017-2018 | per audit | 2 | 15000 | 30000 |  | 0 |  | 0 | 0 | 0 |  | 0
Financial &Accounting Software | per SW | 1 | 25000 | 25000 |  | 0 |  | 0 | 0 | 0 |  | 0
M&E Software | per SW | 1 | 20000 | 20000 |  | 0 |  | 0 | 0 | 0 |  | 0
Development of M&E Plan | per Plan | 1 | 7000 | 7000 |  | 0 |  | 0 | 0 | 0 |  | 0
Procedure Manual | Per manuel | 1 | 25000 | 25000 |  | 0 |  | 0 | 0 | 0 |  | 0
4. Operation costs |  | 248.333 | 990.6051 | 245999.94 | 6.403% | 31322.66 | 4601 | 24136.42 | 28737.42 | 60060.08 | 2760 | 62820.08
Travel (flight ticket) | Travel | 38 | 1000 | 38000 |  |  | 336 | 5175.19 | 5511.19 | 5511.19 | 2760 | 8271.19
Travel (DSA) | DSA | 183.333 | 180 | 32999.94 |  |  |  | 6723.23 | 6723.23 | 6723.23 |  | 6723.23
HPC operation | per Month | 12 | 4000 | 48000 |  |  |  |  | 0 | 0 |  | 0
Consummable (elect,fuel, internet | per Month | 12 | 6000 | 72000 |  | 4455.48 | 4265 | 12238 | 16503 | 20958.48 |  | 20958.48
2nd Steering committee meeting | per stereering | 1 | 40000 | 40000 |  | 26867.18 |  |  | 0 | 26867.18 |  | 26867.18
Mid term meeting |  | 1 | 15000 | 15000 |  |  |  |  | 0 | 0 |  | 0
ACMAD contribt |  |  |  | 134461 | 3.5% | 14939266% |  |  | 0 | 149392.66 | 0 | 149392.66
ACMAD contribt in Kind | room,pers, maeriel | 1 | 1 | 134461 |  | 45817 | 22333 | 29777 | 52110 | 97927 |  | 97927
Total budget |  |  |  | 3841760.94 | 100% | 195209.66 | 146485 | 235032.42 | 381517.42 | 576727.08 | 87444 | 664171.08
Efdb contribution
ACMAD contribution in Kind
Total 2018 Budget

## suivi 2018
2- 2018: xécution budgétaire2017-2018 Budget par categories
Categories |  |  |  | Unit | # of units | Unit rate | Total Cost | Percent of the total | Exécution 2017 | Exécution 2018 1 | Exécution 2018 2 | Exécution 2018 globale | Exécution 2017-2018 globale | Engagements
|  |  | budget projet |  |  | (in EUR) | (in EUR)3
1.PERSONNEL
1.1 Salaries |  |  |  | Per month | 132 | 3072.7273 | 405600 | 10.56% |  | 93080 | 115970 | 209050 | 209050 | 19230 | 228280
1.1.1 Technical |  |  |  | Per month | 60 | 3380 | 202800 | 5.279% |  | 42380 | 58870 | 101250 | 101250 | 8730 | 109980
IT/RARS Expert | 36 | 3500 |  | Per month | 12 | 3500 | 42000 |  |  | 10500 | 12189 | 22689 | 22689 | 1811 | 24500
NWP FORECASTER | 4 | 4000000 |  | Per month | 12 | 3500 | 42000 |  |  | 10500 | 12177 | 22677 | 22677 | 1823 | 24500
NWP FORECASTER ASSISTANT |  |  |  | Per month | 12 | 2500 | 30000 |  |  | 7500 | 8821 | 16321 | 16321 | 1179 | 17500
NWP modeller |  |  |  | Per month | 12 | 3900 | 46800 |  |  | 3380 | 13506 | 16886 | 16886 | 2094 | 18980
NWP System Engineer/IT specialist |  |  |  | Per month | 12 | 3500 | 42000 |  |  | 10500 | 12177 | 22677 | 22677 | 1823 | 24500
1.1.2 Administrative/ support staff |  |  |  | Per month | 72 | 2816.6667 | 202800 | 5.279% |  | 50700 | 57100 | 107800 | 107800 | 10500 | 118300
Project Manager |  |  |  | Per month | 12 | 4100 | 49200 |  |  | 12300 | 12300 | 24600 | 24600 | 4100 | 28700 | 10.56% | 405600
project Assistant |  |  |  | Per month | 12 | 2200 | 26400 |  |  | 6600 | 7700 | 14300 | 14300 | 1100 | 15400 | 58.83% | 2260000
Monitoring & évaluation Officer |  |  |  | Per month | 12 | 2700 | 32400 |  |  | 8100 | 9450 | 17550 | 17550 | 1350 | 18900 | 20.71% | 795700
Finance & Administration Officer |  |  |  | Per month | 12 | 2700 | 32400 |  |  | 8100 | 9450 | 17550 | 17550 | 1350 | 18900 | 6.403% | 245999.94
Procurement Spécialist |  |  |  | Per month | 12 | 2700 | 32400 |  |  | 8100 | 9450 | 17550 | 17550 | 1350 | 18900 | 3.5% | 134461
Communication Officer |  |  |  | Per month | 12 | 2500 | 30000 |  |  | 7500 | 8750 | 16250 | 16250 | 1250 | 17500 | 100% | 3841760.94
2. GOODS |  |  |  |  | 11 | 205454.5455 | 2260000 | 58.83% |  | 0 | 0 | 0 | 0 | 0 | 0
Preparation of the RARS hosting site infrastructure and establishing MoU with hosting sites |  |  |  | per Site | 4 | 10000 | 40000 |  |  | 0 | 0 | 0 | 0 |  | 0
Procurement and instalation of antenna |  |  |  | per antenna | 4 | 400000 | 1600000 |  |  | 0 | 0 | 0 | 0 |  | 0
Procurement and installation of NWP hardware and software infrastructure (HPC system and customized software) |  |  |  | Full system | 1 | 600000 | 600000 |  |  | 0 | 0 | 0 | 0 |  | 0
Customised SW |  |  |  | per SW | 2 | 10000 | 20000 |  |  | 0 | 0 | 0 | 0 |  | 0
3. SERVICES |  |  |  |  | 51 | 15601.9608 | 795700 | 20.71% |  | 26471 | 65149 | 91620 | 91620 | 65454 | 157074
RARS Expert (Technical Assistance) |  |  |  | per Month | 12 | 9000 | 108000 |  |  | 0 | 0 | 0 | 0 |  | 0
NWP Expert (Technical Assistant) |  |  |  | per Month | 12 | 9000 | 108000 |  |  | 0 | 0 | 0 | 0 |  | 0
RARS Design study |  |  |  | per study | 1 | 120000 | 120000 |  |  | 0 | 6670 | 6670 | 6670 | 65454 | 72124
HPC maintenance |  |  |  | Per year | 1 | 20000 | 20000 |  |  |  |  | 0 | 0 |  | 0
NWP related Telecommunication |  |  |  | per Month | 12 | 2500 | 30000 |  |  |  | 3078 | 3078 | 3078 |  | 3078
Training for trainers |  |  |  | Training package | 1 | 12000 | 12000 |  |  |  |  | 0 | 0 |  | 0
NWP forum |  |  |  | per forum | 1 | 173500 | 173500 |  |  | 2618 | 30139 | 32757 | 32757 |  | 32757
DRR Specialist outlook forum |  |  |  | per forum | 1 | 17100 | 17100 |  |  | 17100 |  | 17100 | 17100 |  | 17100
Product Harmonisation meeting |  |  |  | per meeting | 1 | 17100 | 17100 |  |  |  |  | 0 | 0 |  | 0
Data Assimilationand NWP Training |  |  |  | per training | 1 | 54000 | 54000 |  |  | 6753 | 18935 | 25688 | 25688 |  | 25688
Value Added Training for DRR specialist |  |  |  | per training | 1 | 19000 | 19000 |  |  |  |  | 0 | 0 |  | 0
Communication & WEB site service |  |  |  | Per year | 1 | 10000 | 10000 |  |  | 0 | 6327 | 6327 | 6327 |  | 6327
Financial audit 2017-2018 |  |  |  | per audit | 2 | 15000 | 30000 |  |  |  | 0 | 0 | 0 |  | 0
Financial &Accounting Software |  |  |  | per SW | 1 | 25000 | 25000 |  |  |  | 0 | 0 | 0 |  | 0
M&E Software |  |  |  | per SW | 1 | 20000 | 20000 |  |  |  | 0 | 0 | 0 |  | 0
Development of M&E Plan |  |  |  | per Plan | 1 | 7000 | 7000 |  |  |  | 0 | 0 | 0 |  | 0
Procedure Manual |  |  |  | Per manuel | 1 | 25000 | 25000 |  |  |  | 0 | 0 | 0 |  | 0
4. Operation costs |  |  |  |  | 248.333 | 990.6051 | 245999.94 | 6.403% |  | 4601 | 24136.42 | 28737.42 | 28737.42 | 2760 | 31497.42
Travel (flight ticket) |  |  |  | Travel | 38 | 1000 | 38000 |  |  | 336 | 5175.19 | 5511.19 | 5511.19 | 2760 | 8271.19
Travel (DSA) |  |  |  | DSA | 183.333 | 180 | 32999.94 |  |  |  | 6723.23 | 6723.23 | 6723.23 |  | 6723.23
HPC operation |  |  |  | per Month | 12 | 4000 | 48000 |  |  |  |  | 0 | 0 |  | 0
Consummable (elect,fuel, internet |  |  |  | per Month | 12 | 6000 | 72000 |  |  | 4265 | 12238 | 16503 | 16503 |  | 16503
2nd Steering committee meeting |  |  |  | per stereering | 1 | 40000 | 40000 |  |  |  |  | 0 | 0 |  | 0
Mid term meeting |  |  |  |  | 1 | 15000 | 15000 |  |  |  |  | 0 | 0 |  | 0
ACMAD contribt | [6 empty] | 134461 | 3.5% |  |  |  | 0 | 0 | 2760 | 2760
ACMAD contribt in Kind |  |  |  | room,pers, maeriel | 1 | 1 | 134461 |  |  | 22333 | 29777 | 52110 | 52110 |  | 52110
Total budget | [6 empty] | 3841760.94 | 100% |  | 146485 | 235032.42 | 381517.42 | 381517.42 | 87444 | 468961.42
Efdb contribution | [10 empty] | 381517.42
ACMAD contribution in Kind | [10 empty] | 468961.42
Total 2018 Budget

## suivi 2017
2- 2017 Budget par categories
Costs | Unit | # of units | Unit rate | Total budget | Total Expenditures | Percent of the total
|  |  | (in EUR) | (in EUR)3 | (in EUR)3
1.PERSONNEL
1.1 Salaries | Per month | 66 | 3072.7273 | 202800 | 118070 | 41.49% | 24.7%
1.1.1 Technical | Per month | 30 | 3380 | 101400 | 44000 | 20.74%
IT/RARS Expert | Per month | 6 | 3500 | 21000 | 21000
NWP Forecaster | Per month | 6 | 3500 | 21000 | 8750
NWP Forecaster Assistant | Per month | 6 | 2500 | 15000 | 5500
NWP modeller | Per month | 6 | 3900 | 23400 | 0
NWP System Engineer/IT specialist | Per month | 6 | 3500 | 21000 | 8750
1.1.2 Administrative/ support staff | Per month | 36 | 2816.6667 | 101400 | 74070 | 20.74%
Project Manager | Per month | 6 | 4100 | 24600 | 24600
project Assistant | Per month | 6 | 2200 | 13200 | 13200
Monitoring & évaluation Officer | Per month | 6 | 2700 | 16200 | 6030
Finance & Administration Officer | Per month | 6 | 2700 | 16200 | 16200
Procurement Spécialist | Per month | 6 | 2700 | 16200 | 7290
Communication Officer |  | 6 | 2500 | 15000 | 6750
2. GOODS |  | 4 | 10000 | 40000 | 0 | 8.183%
Preparation of the RARS hosting site infrastructure and establishing MoU with hosting sites | per Site | 4 | 10000 | 40000 | 0
Procurement and installation of NWP hardware and software infrastructure (HPC system and customized software) | Full system | 1 | 0 | 0 | 0
3. SERVICES |  | 13 | 9076.9231 | 118000 | 0 | 24.14%
RARS Expert (Technical Assistance) | per Month | 6 | 9000 | 54000 | 0
NWP Expert (Technical Assistant) | per Month | 6 | 9000 | 54000 | 0
Communication & WEB site service | Per year | 1 | 10000 | 10000 | 0
4. Operation costs |  | 227.333 | 563.0504 | 127999.94 | 31323.67 | 26.19% | 6.553%
Travel (flight ticket) | Travel | 38 | 1000 | 38000 | 0
Travel (DSA) | DSA | 183.333 | 180 | 32999.94 | 0
Consummable | (fuel, vehicle repairs, etc) | 6 | 2000 | 12000 | 3159.67
kick off meeting | per meeting | 1 | 15000 | 15000 | 0
first Steering committee meeting | per meeting | 1 | 30000 | 30000 | 28164
[5 empty] | 45817 | 0%
ACMAD contribt in nature | room,pers, maeriel | 1 | 17728 | 17728 | 45817 |  |  | 488800 | 30.56%
Total 2017budget |  |  |  | 488799.94 | 195210.67 | 39.94% |  | 478000 | 282789.33
Efdb contribution |  |  | 100% | 488800 | 149393.67 | 39.94% |  |  | 31.25%
ACMAD contribution in kind |  |  | 3.627% | 17728 | 5229 |  |  | 97.79%
Total 2017 Budget |  |  | 100% | 506528 | 154622.67
|  |  |  | veh | 9000000
2000000
1000000
6000000
6000000
|  |  |  | djibo | 2501659
|  |  |  | gardien | 1776188
|  |  |  | chauf | 1776138
[5 empty] | 30053985 | 45817.0048

## Feuil1
TABLEAU DES EMPLOIS ET DES RESSOURCES
EMPLOIS
Exercice
en cours
Cumulé
PASSIF
Exercice
en cours
Cumulé
Composantes
Ressources de financement
A
Prêt FAD
Don FAD
B
Fonds de Contrepartie Etat
C
D
F
Autres ressources (dont bénéficiaires)
Dettes à court terme
Valeurs Réalisables
Fournisseurs
Fournisseurs
Personnel
Autres tiers
Personnel
Autres tiers
Valeurs Disponibles
Comptes Spéciaux
Total Actif
Total Passif
ETAT DE RECONCILIATION DU COMPTE SPECIAL
N° ----------------- Exercice-------------
I
FONDS RECUS
TOTAL A
Note 1
DRF N°1
----------------------
DRF N°2
----------------------
DRF N°3
----------------------
TOTAL A
II
DEPENSES JUSTIFIEES
Soumises en justification à la Banque
TOTAL B (EN DEDUCTION)
Note 2
Avec DRF N°2
Avec DRF N°3
TOTAL B
Rejetées par la Banque
TOTAL C (EN ADDITION)
Note 3
Avec DRF N°2
Avec DRF N°3
TOTAL C
III
DEPENSES NON ENCORE JUSTIFIEES
TOTAL D (EN DEDUCTION)
Note 4
SOLDE THEORIQUE E = (A-B+C-D)
SOLDE REEL
Note 5
Banque - Compte Spécial
Banque - Sous-Comptes
Caisse
TOTAL F
ECART G= (E-F)
Note

## Feuil2
TABLEAU DES EMPLOIS ET DES RESSOURCES PROJET SAWIDRA ACMAD Exercice 2017
EMPLOIS | Exercice en cours | Cumulé | PASSIF | Exercice en cours | Cumulé
Composantes | 195210.67 | 195210.67 | Ressources de financement | 524617 | 524617
I. Establisment of RARS Network | 21000 | 21000 | Fonds CSDF | 478800 | 478800
II. NWP Capabilities at ACMAD | 23000 | 23000 | fonds CSDFde contrepartie | 45817 | 45817
III.NWP Communites | 0 | 0
IV. Project Coordination | 151210.67 | 151210.67 | Autres Ressources | 0 | 0
Contrepatie
Valeurs realisables | 0 | 0 | Dettes à court terme | 0 | 0
Fournisseurs | 0 | 0
Personnel | 0 | 0 | Fournisseurs | 0 | 0
Autres | 0 | 0 | Personnel | 0 | 0
Valeurs disponibles | 329406.41 | 329406.41 | Autres tiers | 0 | 0
Comptes speciaux:
Compte N° 013360078 EURO | 270612.61 | 270612.61
Compte N° 013360078 CFA | 58793.8 | 58793.8
Total Actif | 524617.08 |  | Total Passif | 524617 |  | -0.08

## Feuil3
ETAT DE RECONCILIATION DU COMPTE SPECIAL PROJET SAWIDRA ACMAD Exercice 2017
Compte Spécial BOA N°01336780069 73 EN EURO
Sous Compte Spécial BOA N°01336780057 12 EN XOF
FONDS RECUS |  | TOTAL A | 478800 | Note 1
DRF 1 | 478800
DRF2
Total A | 478800
II. DEPENSES JUSTIFIEES
Soumises en justification à la Banque |  | TOTAL B (en DEDUCTION) | 0 | Note 2
Acceptées par la Banque
avec DRF N° 2
avec DRF N° 3
Total B
Rejetées par la Banque |  | TOTAL C (EN ADDITION) | 0 | Note 3
avec DRF N° 2
avec DRF N° 3
III. DEPENSES NON ENCORE JUSTIFIEES | 149394 | TOTAL D ( EN DEDUCTION) | 149394 | Note 4
|  | SOLDE THEORIQUE E= (A-B+C-D) | 329406 | Note 5
SOLDE REEL
|  | BANQUES | 329406
|  | TOTAL F | 329406
|  | ECART G= (E-F) | 0 | Note 5
L'analyse de l'état de reconciliation du compte spécial permet de noter que un seul virement de fonds a été effectue
effectué