| #### CENTRE AFRICAIN POUR LES APPLICATIONS #### DE LA METEOROLOGIE AU DEVELOPPEMENT |  |  | #### AFRICAN CENTRE OF METEOROLOGICAL APPLICATIONS FOR DEVELOPMENT |
| --- | --- | --- | --- |
| Institution Africaine parrainée par la CEA et l’OMM |  | African Institution under the aegis of UNECA and WMO |  |

Annex

UNECA – ACMAD Joint action plan for 2022/23

Start date: 01/01/2022 End date: 31/12/2023

- Introduction and scope

Over the past years, AUC, WMO, UNECA and ACMAD have been operating in collaboration with other partners on the generation, publication and communication of the  annual state of Africa’s climate, design and implementation on climate information and knowledge platform,  development of the Africa strategy on meteorology and monitoring of its implementation together with agenda 2063 and SDGs, organization  of  meetings, workshops and conferences on Climate  and Development in Africa,  development and review of the ACMAD – AUC relationship agreement implementing the relevant  4th AMCOMET declaration in  Cairo. The sections below provide details on future joint actions. This paper describes with details the above-mentioned actions.

- Joint action plan description

- Generation, publication, and communication of the 2022 state of climate for Africa

Based on the network of African and WMO experts’ teams set up in 2021 delivering the 2020 state of climate for Africa, UNECA, AUC and ACMAD will lead relevant sections of the 2021 state of climate report and support review and editing as a contribution to COP 27.   Arrangements with WMO,  AUC , UNECA and ACMAD is to be made by March 2022 to start the preparatory work by mobilizing  lead and contributing experts and agree on the publication mechanism, the tentative date for the launch and follow up communication for African negotiators, UNFCCC SABSTA,  relevant high level Ministerial sessions and Specialized Technical Committees of AUC and UNECA trough statements and presentations, side events, dialogues, discussions and high level statements at the upcoming UNFCCC COP 27 in Charm El Check.

.

- Design and implementation on climate information and knowledge system

UNECA, WMO and ACMAD started collaboration to facilitate access to climate knowledge across Africa through a platform. A concept note with ToRs for a consultant to design and support implementation of the online platform was prepared. Proposed tasks in 2022 and 2023 include the monitoring of the consultant’s work, the review and validation of the platform and planning for regular update responsibilities for the platform.

- Support implementation of AMCOMET strategy, relevant aspects of agenda 2063 and SDG 13

UNECA and ACMAD will collaborate to deliver statements and relevant section of reports and statements to the Conference of Ministers of economy, finance, and planning on climate trends and impacts.  Monitoring of SDGs, AMCOMET strategy indicators and publication in reports will be additional task under this activity.

- Review and approval of the ACMAD – AUC relationship agreement implementing the relevant 4th AMCOMET declaration in Cairo

The 4th AMCOMET declaration in Cairo in February 2019, endorsed the designation of ACMAD as the technical arm of the African Union on climate matters.  A follow up effort leading to a draft relationship agreement was completed by ACMAD, AUC with the support of WMO.  This draft was submitted to UNECA through its West Africa Regional Office.  It is proposed that this draft be reviewed by UNECA and submitted by AUC for endorsement by the next Specialized Technical Committee on Agriculture, Rural Development, Water and Environment.

- Organization of events on Climate and Development in Africa

UNECA and ACMAD will plan and organize the following events:

- Joint meeting in 2022 of experts contributing to physical science and impact section for the Africa region to the IPCC assessment.

- CCDA Conference.

- Joint planning meeting for the year 2023

- Joint high-level dialogue and other events at COP 27