# Terms Of  References for  staff

# Basic Information

| # Requesting agency | # ACMAD | # Country | # NIGER |
| --- | --- | --- | --- |
| # Duty station | # NIAMEY | Security phase in # Country / duty station | # 3 moderate |
| # Start date for the financial year | # January , 2021 | # Expected duration of activities during the year | # 12 months |
| # First year of activity # (Indicate with Yes/No) | # No | # If No, how many years or mothns already spent on this position | # 19 months |

## Please provide name, title, telephone number and e-mail address

| Supervisor’s Name | Dr. Elijah ADEFISAN |
| --- | --- |
| # Supervisor’ s email& phone | # eaelijah@acmad.org # +227793787346 |
| ACMAD focal point for secretariat&administrative issues– contact for visa, security clearance, airport pick-up, hotel booking etc | # Safiia Alfa ( ACMAD Secretariat) # Nafissa Moussa ( Human Resources Officer) |

Background information/reason for request/extension

| - Current situation at ACMAD - Existing programme strategies and mechanism - Current internal staffing capacity - Other info | ACMAD is a WMO Regional Climate Centre for all Africa with mandatory and recommended functions. The WMO Regional Association of African National Meteorological and Hydrological Services added the coordination function of Regional Climate Centers in Africa. African countries are requesting climate change information to craft and implement adaptation and resilience projects. ACMAD is collecting climate change assessment datasets including global and regional projections, developing tools and methods for climate change assessments at regional level. The deployee will update products, methods and tools through literature review and apply for climate scenarios provision tailored to agriculture, water and disaster risk management sectors. Technical notes, bulletins, reports and summary or statements on climate monitoring, forecasting and assessments are expected. 20 staff members work at ACMAD with 4 in the Department that will host the deployee. Most African National Meteorological and Hydrological Services(NMHSs) rely on technical partners to provide climate scenarios for national use. The deployee will be involved in training NMHSs to develop and improve capacity on climate change assessments. |
| --- | --- |

Terms of Reference for the  Staff

| - Title and level of staff - Objectives and expected output - Main duties and responsibilities - Reporting and supervision | Name of staff: Dr. Victor Indasi Role Title: Research Scientist: Weather and Climate Services Objectives: The GCRF African-SWIFT consortium, led by the National Centre for Atmospheric Science (NCAS), builds upon existing partnerships between forecasting centres and universities in four African partner countries – Senegal, Ghana, Nigeria and Kenya – bringing together 5 UK partners (NCAS, University of Leeds, University of Reading, CEH, UK Met Office), 10 African Partners (ACMAD, ICPAC, ANACIM, UCAD, GMet, KNUST, NiMet, FUTA, KMet and University of Nairobi) and the UN World Meteorological Organisation (WMO). Over the 4 year programme, the team of 25 UK and 45 African atmospheric scientists, social scientists and operational forecasters will undertake fundamental scientific research into the physics of tropical weather systems; evaluation and presentation of complex model and satellite data; and communication and exploitation of forecasts. The GCRF African-SWIFT team will work with forecast users across sectors from aviation to agriculture, energy, water and emergency response to understand how to tailor the provision and delivery of weather forecasts and to ensure improved response to high-impact events (e.g. onset of rains, heat-waves, dry spells, strong winds); rapid emergency response to extreme events, such as urban flooding and prolonged droughts; and increased resilience, through integration of weather prediction into strategies for response to climate change. GCRF African-SWIFT will: - Make fundamental research advances to significantly improve weather forecasts in Africa, and the tropics more generally, from the hourly to the seasonal timescale. - Build the operational capability of the African forecast agencies; deliver state-of-the-art forecasting tools; and improve links and communication with forecast users. - Assist African partners in developing capacity for sustained training of forecasters, in partnership with African academic institutions and international agencies to yield ongoing forecasting improvements in the coming decades. - Ensure results are translatable beyond the partner countries to other nations of Africa and the developing world more widely. - Deliver an impact felt by many millions of ordinary African people, and by large public and private-organisations across sectors from aviation to agriculture, energy, water and emergency response. Under the immediate supervision of the Programme Science Director of the Science for Weather Information and Forecasting Techniques (SWIFT) Programme and the overall supervision of the Director General of ACMAD, Research Scientist: Weather and Climate Services will be responsible for environmental social science research activities and some of the training elements of the SWIFT Programme. The Researcher will help in the identification of user needs, co-production and communication for climate and weather services focusing on both West Africa and Kenya. The Researcher will be based in the new to be established Research and Development Department of ACMAD, but will work in close collaboration with researchers at the University of Leeds, UK and at Kwame Nkrumah University of Science and Technology, Ghana, as well as SWIFT partners in Senegal, Nigeria, Ghana and Kenya. A key part of the role will involve taking the lead in planning and organizing participatory workshops. In line with the above, the incumbent will: - Work with the GCRF African SWIFT project team to ensure that outputs for Work Package 1: user needs, co-production and communication are delivered. - Share and report on findings across a large consortium, with members from different countries and disciplines. - Work with partner organizations in Senegal, Nigeria, Ghana and Kenya to map the current provider and user landscape for weather and climate information services. - Conduct interviews with users (and potential users) of climate and weather services in partner countries. - Lead the planning and organization of participatory stakeholder workshops. - Work with providers and users of weather information in partner countries to identify more effective strategies for forecast communication. - Feedback views of user community to GCRF African-SWIFT consortium members. - Contribute to setting the direction of the research project and team. - Evaluate methods and techniques used and results obtained by other researchers and relate such evaluations appropriately to your own work. - Ensure the production and presentation of information at conferences. - Contribute to peer-reviewed publications. - Embed research results into operational practice documents to promote the training of African scientists and strengthen the capabilities of the national meteorological services. - Lead on the organization and delivery of some of the SWIFT African meteorological practice and testbed training events. - Assist the Program Science Director and Heads of Departments in ACMAD in the monitoring of trainees under Weather related, Climate related, meteorological applications, training and strengthening capacity programme. - Perform any duty that may be assigned to him or her in line with the activities and operations of ACMAD. - Quartely progress reported authored by the Research Scientist, reviewed and signed by the supervisor. - Quartely activity schedules produced by the Research Scientist, reviewed and signed by the supervisor. - Performance evaluation form produced by the Research Scientist, reviewed and signed by the supervisor. - Mission reports produced by the Research Scientist, reviewed and signed by the supervisor. |
| --- | --- |
| - Deliverables | - D-R1.2: Paper: - SWIFT country User Surveys and Interviews - D-C2.4: Documentation on Testbed 2. Papers. - D-C2.3: Carry out S2S Testbed. - D-C2.5: Carry out Testbed 3. - D-R1.3: Coproduced forecast communication tools that have been iteratively tested and refined with user groups, and recommendations for good practice, merged with D-R 6.5. - D-M2.7: Produce a Forecasters' Handbook for East Africa. - White Paper on the Potential of Operational Weather Prediction to save lives and Improve Livelihoods and Economies in Sub-Saharan Africa. |

| # Deliverable/Activities | # Tasks | # Lead/C | # J | # F | # M | # A | # M | # J | # J | # A | # S | # O | # N | # D |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D-R1.2: Paper: - SWIFT country User Surveys and Interviews | # Literature review | # L |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Data Analysis | # L |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Manuscript drafting | # L |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # First complete nanuscript for inhouse sharing | # L |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Editing, proof-reading and corrections | # L |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Final manuscript for submission | # L |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Reviewer comments and publishing | # L |  |  |  |  |  |  |  |  |  |  |  |  |
| D-C2.4: Documentation on Testbed 2. Papers. | # Paper 1: Documentation for Products developed within the SWIFT | # C |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Paper 2: Meningitis vigilance evaluation. | # C |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Paper 3: Progress and challenges of demand-led co-produced subseasonal-to-seasonal (S2S) climate forecasts in Nigeria. | # C |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Manuscript drafting | # C |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # First complete nanuscript for inhouse sharing | # C |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Editing, proof-reading and corrections | # C |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Final manuscripts for submission | # C |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Reviewer comments and publishing | # C |  |  |  |  |  |  |  |  |  |  |  |  |
| D-C2.3: Carry out S2S Testbed. | # Testbed monthly co-production meetings | # C |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Quarterly producer and user questionnare administration | # C |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Quarterly producer and user survey data analysis | # C |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Producer and user survey reports | # C |  |  |  |  |  |  |  |  |  |  |  |  |
| D-C2.5: Carry out Testbed 3. | # Testbed 3 management team monthly meetings | # C |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Testbed 3 Users & Co-production Workgroup monthly meetings | # L |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Testbed 3 Users & Co-production workshop | # L |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Testbed 3 Users & Co-production workshop report | # L |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Testbed 3 | # C |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Testbed 3 report | # C |  |  |  |  |  |  |  |  |  |  |  |  |
| D-R1.3: Coproduced forecast communication tools that have been iteratively tested and refined with user groups, and recommendations for good practice, merged with D-R 6.5. | # Joint monthly meetings with D-R6.6 | # L |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Bi-annual questionnaire administration | # L |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Transcribing recorded surveys | # L |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Data analysis | # L |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Report drafting | # L |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Report review and submission | # L |  |  |  |  |  |  |  |  |  |  |  |  |
| D-M2.7: Produce a Forecasters' Handbook for East Africa. | # Review of Forecasters' Handbook for East Africa chapters | # C |  |  |  |  |  |  |  |  |  |  |  |  |
| # White Paper on the Potential of Operational Weather Prediction to save lives and Improve Livelihoods and Economies in Sub-Saharan Africa. | # Monthly meetings | # C |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Manuscript chapter drafting – communication and delivery of forecasts | # L |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Manuscript editing, proof-reading and corrections | # C |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Final manuscript for submission | # C |  |  |  |  |  |  |  |  |  |  |  |  |
|  | # Reviewer comments and publishing | # C |  |  |  |  |  |  |  |  |  |  |  |  |

# Other relevant information

# None